## Sheet1
Name | Start Date | End Date | Duration | Projects | Comments
Mock-Up |  |  |  | Sundry HR Recruitment Portal | DONE
Mock-Up Design. |  |  |  | Sundry HR Recruitment Portal | DONE
Review and approve mock-up. |  |  |  | Sundry HR Recruitment Portal | DONE
Applicant Portal Module (Stage 1) |  |  |  | Sundry HR Recruitment Portal | DONE
Prospective Applicant to search Job by title. |  |  |  | Sundry HR Recruitment Portal | DONE
Prospective Applicant to search Job by location. |  |  |  | Sundry HR Recruitment Portal | DONE
Prospective Applicant to search by keywords. |  |  |  | Sundry HR Recruitment Portal | DONE
Applicant Portal Module (Stage 2) |  |  | 7 | Sundry HR Recruitment Portal | DONE
Design and Implement applicant Login | 2019-05-13 | 2019-05-14 | 1 | Sundry HR Recruitment Portal | DONE
Design and Implement Answer, Submit CBT and Get Score | 2019-05-15 | 2019-05-19 | 4 | Sundry HR Recruitment Portal | Initially built but customer requested a different implementation. (Assigned to Dozie)
Design and Implement applicant video upload | 2019-05-20 | 2019-05-22 | 2 | Sundry HR Recruitment Portal | DONE
Applicant Portal Module (Stage 3) |  |  | 3 | Sundry HR Recruitment Portal
Design and Implement function for applicant to view interview information (type, location, date, requirements). | 2019-05-23 | 2019-05-24 | 1 | Sundry HR Recruitment Portal | DAVE TO IMPLEMENT
Design and Implement function for applicant to view evaluation feedback where applicable. | 2019-05-25 | 2019-05-26 | 1 | Sundry HR Recruitment Portal | DAVE TO IMPLEMENT
Design and Implement function for applicant to view, sign and accept offers. | 2019-05-27 | 2019-05-28 | 1 | Sundry HR Recruitment Portal | FRANCIS (16th August), Dave (16th August)
Admin Portal Module (Stage 1) |  |  | 12 | Sundry HR Recruitment Portal
Design and Implement function to Add, Update, set hiring goal (time or number of applications) and choose workflow for job listing. | 2019-05-29 | 2019-05-30 | 1 | Sundry HR Recruitment Portal | DONE
Design and Implement function to Create questions for job roles. | 2019-05-31 | 2019-06-01 | 1 | Sundry HR Recruitment Portal | DONE
Implement sharing of posts to social media (Facebook and LinkedIn). | 2019-06-02 | 2019-06-04 | 2 | Sundry HR Recruitment Portal
Design and Implement viewing of posted job listing on the portal and dashboard. | 2019-06-05 | 2019-06-06 | 1 | Sundry HR Recruitment Portal | DONE
Design and Implement monitoring of applications as they come in. | 2019-06-07 | 2019-06-08 | 1 | Sundry HR Recruitment Portal | DONE
Design and Implement starring (archiving) applications with reasons. | 2019-06-09 | 2019-06-11 | 2 | Sundry HR Recruitment Portal | DONE
Design and Implement searching and filtering applications by keywords. | 2019-06-12 | 2019-06-13 | 1 | Sundry HR Recruitment Portal | DONE
Implement approval of suitable candidates for stage 2. | 2019-06-14 | 2019-06-15 | 1 | Sundry HR Recruitment Portal | DONE
Implement monitoring of candidate progress. | 2019-06-16 | 2019-06-18 | 2 | Sundry HR Recruitment Portal | DONE
Admin Portal Module (Stage 2) |  |  | 5 | Sundry HR Recruitment Portal | DONE
Design and Implement creating, editing and updating CBTs on the platform OR create video interview questions. | 2019-06-19 | 2019-06-21 | 2 | Sundry HR Recruitment Portal | DONE
Implement function for sharing of resumes with hiring managers. | 2019-06-22 | 2019-06-24 | 1 | Sundry HR Recruitment Portal | DONE
Implement function for approval of candidate for Stage 3 (Interview). | 2019-06-25 | 2019-06-27 | 2 | Sundry HR Recruitment Portal | DONE
Admin Portal Module (Stage 3) |  |  | 17 | Sundry HR Recruitment Portal
Design and Implement creating, editing and updating interview scorecard/job preview template on the platform. | 2019-06-28 | 2019-06-30 | 2 | Sundry HR Recruitment Portal | DAVE TO IMPLEMENT
Implement sharing of resumes with hiring managers for final interview selection. | 2019-07-01 | 2019-07-02 | 1 | Sundry HR Recruitment Portal | DONE
Implement approval of candidates for interview and interview type. | 2019-07-03 | 2019-07-05 | 2 | Sundry HR Recruitment Portal | DONE
Implement notification of hiring manager and other interview panelists for interviews. | 2019-07-06 | 2019-07-07 | 2 | Sundry HR Recruitment Portal | DONE
Design and Implement creating and updating of hiring notes. | 2019-07-08 | 2019-07-10 | 2 | Sundry HR Recruitment Portal | DONE
Design and Implement creating, editing and updating of offer acceptance templates. | 2019-07-11 | 2019-07-13 | 2 | Sundry HR Recruitment Portal | DONE
Implement extending of offers directly to successful candidates. | 2019-07-14 | 2019-07-15 | 1 | Sundry HR Recruitment Portal | DONE
Implement recruitment of applicant with just the click of a button. |  |  | 0 | Sundry HR Recruitment Portal | DONE
Implement routing of candidate to practical evaluation module. | 2019-07-16 | 2019-07-18 | 2 | Sundry HR Recruitment Portal | FRANCIS and DAVE
Design and Implement evaluation functions from Job Preview Evaluators. | 2019-07-19 | 2019-07-22 | 3 | Sundry HR Recruitment Portal | DAVE and DOZIE
Other Functions |  |  | 5 | Sundry HR Recruitment Portal
Implement duplicate detection: See where a candidate has applied for more than one role or more than one time in a space of 6 months. | 2019-07-23 | 2019-07-25 | 2 | Sundry HR Recruitment Portal | API READY DAVE TO IMPLEMENT
Design and Implement creating and updating feedback templates. | 2019-07-29 | 2019-07-30 | 1 | Sundry HR Recruitment Portal | DONE
Design and Implement sending of periodic email updates to applicants. | 2019-07-31 | 2019-08-02 | 2 | Sundry HR Recruitment Portal | DONE
Sundry HR Recruitment Portal
Design and Implement Reporting Module |  |  | 9 | Sundry HR Recruitment Portal
Implement pipeline Per Job report. | 2019-07-26 | 2019-07-28 | 2 | Sundry HR Recruitment Portal | DONE
Report: number of new hires (monthly), number of applications (monthly) per job, most frequently applied job and least frequently applied jobs. | 2019-07-29 | 2019-07-31 | 2 | Sundry HR Recruitment Portal | DONE
Number of unsuccessful vs successful candidates. | 2019-08-01 | 2019-08-02 | 1 | Sundry HR Recruitment Portal
Design and implement viewing of consolidated reports. | 2019-08-03 | 2019-08-07 | 4 | Sundry HR Recruitment Portal
| Total |  | 55
Formulas:
End Date = [Start Date]+[Duration]
End Date = [Start Date]+ [Duration]
Start Date = [End Date, row above]+1

## Sheet2
Name | Start Date | End Date | Duration(days) | Projects | Comments
Mock Up |  |  |  | Queue Management System | Done
Mock Up Design |  |  |  | Queue Management System | Done
Review and approve mock-up. | 13/09/2019 | 14/09/2019 | 1 | Queue Management System
Store Front |  |  |  | Queue Management System
Design of Order Queue board | 16/09/2019 | 17/09/2019 | 1 | Queue Management System
API integration of order status(to display on board) | 17/09/2019 | 18/09/2019 | 1 | Queue Management System
Kitchen(Admin) |  |  |  | Queue Management System
Design(frontend) and implement(backend) form for order details (Cashier end) | 18/09/2019 | 20/09/2019 | 2 | Queue Management System
Design of admin interface | 20/09/2019 | 21/09/2019 | 1 | Queue Management System
Implement viewing of orders as they come in (frontend and backend) | 23/09/2019 | 25/09/2019 | 2 | Queue Management System
Implement update of order status (frontend and backend) | 25/09/2019 | 27/09/2019 | 2 | Queue Management System
Implement removal of order from queue on completion(frontend and backend) | 27/09/2019 | 28/09/2019 | 1 | Queue Management System
Implement process time count down(frontend and backend) | 28/09/2019 | 30/09/2019 | 2 | Queue Management System
Extras
Application review and testing
Documentation (Manual)
|  | Total | 12